## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Team
| Table 1 | Team
Backlog
| Table 1 | Backlog
Burndown README
| Table 1 | Burndown README
Burndown
| Table 1 | Burndown
Sprint1
| Table 1 | Sprint1
Sprint2
| Table 1 | Sprint2
Sprint3
| Table 1 | Sprint3
Sprint4
| Table 1 | Sprint4
Stories
| Table 1 | Stories

## Team
Initials | First | Last | Email | GitHub Username
hl | Hanqing | Liu | hliu69@gmail.com | HanQLiu
hrl | Haoran | Li | hli121@stevens.edu | xeal3k
jm | Jigar | Masekar | jmasekar@stevens.edu | JMasekar
sd | Shengda | Zhang | szhang14@stevens.edu | shengda567
xw | Xiangyu | Wang | xwang173@stevens.edu | 769978445
|  |  | GitHub Repository: | https://github.com/HanQLiu/555-GED-Project (main working repository)
https://github.com/HanQLiu/555-Project (sprint 1 old repository )

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | hl | Complete
1 | US02 | Birth before marriage | hl | Complete
2 | US03 | Birth before death | hl | Complete
2 | US08 | Birth before marriage of parents | hl | Complete
3 | US09 | Birth before death of parents | hl | Complete
3 | US16 | Male last names | hl | Complete
4 | US23 | Unique name and birth date | hl | Complete
4 | US28 | Order siblings by age | hl | Complete
1 | US11 | No bigamy | hlr | Complete
1 | US12 | Parents not too old | hlr | Complete
2 | US13 | Siblings spacing | hlr | Complete
2 | US14 | Multiple births <= 5 | hlr | Complete
3 | US18 | Siblings should not marry | hlr | Complete
3 | US19 | First cousins should not marry | hlr | Complete
4 | US20 | Aunts and uncles | hlr | Complete
4 | US21 | Correct gender for role | hlr | Complete
1 | US04 | Marriage before divorce | jm | Complete
1 | US06 | Divorce before death | jm | Complete
2 | US17 | No marriages to children | jm | Complete
2 | US22 | Unique IDs | jm | Complete
3 | US25 | Unique first names in families | jm | Complete
3 | US27 | Include individual ages | jm | Complete
4 | US29 | List deceased | jm | Complete
4 | US30 | List living married | jm | Complete
1 | US05 | Marriage before death | sd | Complete
1 | US07 | Less then 150 years old | sd | Complete
2 | US10 | Marriage after 14 | sd | Complete
2 | US31 | List living single | sd | Complete
3 | US35 | List recent births | sd | Complete
3 | US36 | List recent deaths | sd | Complete
4 | US37 | List recent survivors | sd | Complete
4 | US38 | List upcoming birthdays | sd | Complete
1 | US15 | Fewer than 15 siblings | xw | Complete
1 | US24 | Unique families by spouses | xw | Complete
2 | US26 | Corresponding entries | xw | Complete
2 | US32 | List multiple births | xw | Complete
3 | US33 | List orphans | xw | Complete
3 | US34 | List large age differences | xw | Complete
4 | US39 | List upcoming anniversaries | xw | Complete
4 | US40 | Include input line numbers | xw | Complete

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Initial |  | 40 | 0 | 0 | 0
Sprint 1 | 2020-02-11 | 30 | 10 | 200 | 10080 | 1.1905
Sprint 2 | 2020-03-03 | 20 | 10 | 152 | 7320 | -0.3
Sprint 3 | 2024-03-01 | 10 | 10 | 174 | 3960 | 0.3
Sprint 4 | 2020-06-04 | 0 | 10 | 208 | 4800 | 0.4

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Completed Source File | Source Function | Test File | Test Function
US01 | Dates before current date | hl | Coded | 20 | 2 | 10 | 4 | 2nd March | Project03CornerStone.py | dates_before_current_date | US01_02_test.py | test_us_01_02
US02 | Birth before marriage | hl | Coded | 20 | 2 | 33 | 4 | 2nd March | Project03CornerStone.py | birth_before_marriage | US01_02_test.py | test_us_01_02
US04 | Marriage before divorce | jm | Coded | 40 | 50 | 15 | 48 | 2nd March | Project03CornerStone.py | marriage_before_divorce | US04_06_TEST.py | test_Marriage_before_divorce
US05 | Marriage before death | sd | Coded | 50 | 15 | 26 | 17 | 2nd March | Project03CornerStone.py | marriage_before_death | Test_case_us05_us07.py | test_US05
US06 | Divorce before death | jm | Coded | 60 | 50 | 12 | 48 | 2nd March | Project03CornerStone.py | divorce_before_death | US04_06_TEST.py | test_Divorce_before_death
US07 | Less then 150 years old | sd | Coded | 50 | 15 | 25 | 17 | 2nd March | Project03CornerStone.py | less_150_years_old | Test_case_us05_us07.py | test_US07
US11 | No bigamy | hlr | Coded | 100 | 2 | 26 | 5 | 2nd March | Project03CornerStone.py | us_11 | Test11And12.py | test_US11
US12 | Parents not too old | hlr | Coded | 100 | 2 | 27 | 5 | 2nd March | Project03CornerStone.py | us_12 | Test11And12.py | test_US12
US15 | Fewer than 15 siblings | xw | Coded | 60 | 12 | 10 | 10 | 2nd March | Project03CornerStone.py | fewer_than_15_siblings | Test_US15_US24.py | test_US15
US24 | Unique families by spouses | xw | Coded | 60 | 12 | 16 | 10 | 2nd March | Project03CornerStone.py | unique_families_by_spouses | Test_US15_US24.py | test_US24
[6 empty] | 200 | 168
Review Results
Improve coordination
Improve communication
Improve planning
Avoid last minute hassle

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Completed Source File | Source Function | Test File | Test Function
US03 | Birth before death | hl | Coded | 30 | 3 | 7 | 4 | 23rd March | The_Real_Project03.py | birth_before_death | Test_for_Sprint_2_HanqingLiu.py | test_birth_before_death
US08 | Birth before marriage of parents | hl | Coded | 30 | 3 | 8 | 4 | 23rd March | The_Real_Project03.py | birth_before_marriage_of_parents | Test_for_Sprint_2_HanqingLiu.py | test_birth_before_marriage_of_parents
US10 | Marriage after 14 | sd | Coded | 50 | 20 | 24 | 18 | 23rd March | The_Real_Project03.py | marriage_after_14 | Test_case_us10_us31.py | test_US10
US13 | Siblings spacing | hlr | Coded | 90 | 4 | 13 | 6 | 23rd March | The_Real_Project03.py | siblings_spacing | Test_sprint2.py | test
US14 | Multiple births <= 5 | hlr | Coded | 90 | 4 | 16 | 6 | 23rd March | The_Real_Project03.py | mutiple_birth | Test_sprint2.py | test
US17 | No marriages to children | jm | Coded | 70 | 25 | 10 | 22 | 23rd March | The_Real_Project03.py | no_marriage_to_children | Test_US17_US22.py | test_US17
US22 | Unique IDs | jm | Coded | 80 | 25 | 17 | 14 | 23rd March | The_Real_Project03.py | unique_ids | Test_US17_US22.py | test_US22
US26 | Corresponding entries | xw | Coded | 40 | 14 | 26 | 16 | 23rd March | The_Real_Project03.py | corresponding_entries | Test_US26_US32.py | test_US26
US31 | List living single | sd | Coded | 50 | 20 | 20 | 17 | 23rd March | The_Real_Project03.py | list_living_single | Test_case_us10_us31.py | test_US31
US32 | List multiple births | xw | Coded | 50 | 14 | 11 | 15 | 23rd March | The_Real_Project03.py | list_multiple_births | Test_US26_US32.py | test_US32
[6 empty] | 152 | 122
Review Results
Improve planning
Avoid last minute hassle

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Completed Source File | Source Function | Test File | Test Function
US09 | Birth before death of parents | hl | Coded | 20 | 4 | 15 | 5 | 6th April | The_Real_Project03.py | birth_before_parents_death | Sprint03_US09_US16_test.py | test_us09_us16
US16 | Male last names | hl | Coded | 20 | 4 | 11 | 4 | 6th April | The_Real_Project03.py | male_last_names | Sprint03_US09_US16_test.py | test_us09_us16
US18 | Siblings should not marry | hrl | Coded | 25 | 5 | 15 | 4 | 6th April | The_Real_Project03.py | sibling_not_marry | Test_Sprint3.py | test
US19 | First cousins should not marry | hrl | Coded | 25 | 5 | 35 | 6 | 6th April | The_Real_Project03.py | first_cousin_not_marry | Test_Sprint3.py | test
US25 | Unique first names in families | jm | Coded | 20 | 8 | 11 | 9 | 6th April | The_Real_Project03.py | unique_first_name | test_sprint3.py | test_US25
US27 | Include individual ages | jm | Coded | 20 | 8 | 7 | 8 | 6th April | The_Real_Project03.py | include_individual_ages | test_sprint3.py | test_US27
US33 | List orphans | xw | Coded | 30 | 7 | 23 | 8 | 6th April | The_Real_Project03.py | list_orphans | Test_US33_US34.py | test_US33
US34 | List large age differences | xw | Coded | 30 | 7 | 16 | 6 | 6th April | The_Real_Project03.py | list_large_age_differences | Test_US33_US34.py | test_US34
US35 | List recent births | sd | Coded | 15 | 6 | 21 | 7 | 6th April | The_Real_Project03.py | List_recent_births | Test_US35_US36.py | test_US35
US36 | List recent deaths | sd | Coded | 15 | 6 | 20 | 8 | 6th April | The_Real_Project03.py | List_recent_deaths | Test_US35_US36.py | test_US36
[6 empty] | 174 | 65
Review Results
Try organising the contents in GitHub repository
Make sure all previous user stories execute properly with the refactored code

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed | Completed Source File | Source Function | Test File | Test Function
US20 | Aunts and uncles | hlr | Coded | 15 | 8 | 21 | 8 | 20th April | The_Real_Project03.py | Aunts_Uncles | Test_Sprint4.py | test
US21 | Correct gender for role | hlr | Coded | 17 | 8 | 10 | 8 | 20th April | The_Real_Project03.py | Correct_gender | Test_Sprint4.py | test
US23 | Unique name and birth date | hl | Coded | 25 | 5 | 22 | 6 | 20th April | The_Real_Project03.py | unique_name_and_birth_date | Test_US23_US28.py | test_US23
US28 | Order siblings by age | hl | Coded | 20 | 5 | 34 | 6 | 20th April | The_Real_Project03.py | order_siblings_by_age | Test_US23_US28.py | test_US28
US29 | List deceased | jm | Coded | 20 | 10 | 19 | 10 | 20th April | The_Real_Project03.py | list_deceased | test_Sprint4.py | test_US29
US30 | List living married | jm | Coded | 20 | 10 | 18 | 11 | 20th April | The_Real_Project03.py | list_living_married | test_Sprint4.py | test_US30
US37 | List recent survivors | sd | Coded | 15 | 6 | 31 | 5 | 20th April | The_Real_Project03.py | List_recent_survivors | Test_US37_US38.py | test_US37
US38 | List upcoming birthdays | sd | Coded | 15 | 6 | 19 | 5 | 20th April | The_Real_Project03.py | List_upcoming_birthdays | Test_US37_US38.py | test_US38
US39 | List upcoming anniversaries | xw | Coded | 25 | 8 | 20 | 7 | 20th April | The_Real_Project03.py | List_upcoming_anniversaries | Test_US39_US40.py | test_US39
US40 | Include input line numbers | xw | Coded | 30 | 12 | 14 | 14 | 20th April | The_Real_Project03.py | Include_input_line_numbers | Test_US39_US40.py | test_US40
[6 empty] | 208 | 80
Review Results
Successfully executed all the user stories
Organised all the files in the GitHub repository

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to children | Parents should not marry any of their children
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)